## Slide 1: Pulse Polio National Immunization Day (NID) 3rd February 2019
Timeline for Districts

## Slide 2
  <20/12/18 – District IPPI workshops / Micro-planning meetings / Urban Area planning meetings
  <31/12/18 – HRA identification, Validation, inclusion by Health workers
  <04/01/19– District level review of all PHC/ UHC Micro-plans
  <11/01/19 - Micro-plans Submission to State
  <31/12/18 – DTF1 & TTF1 meetings
  <26/01/19 – DTF2 & TTF2 meeting
  <26/01/19 –Supervisors training
  <26/01/19 - Procurement & distribution of vaccine logistics formats & IEC materials
  < 01/02/19 – Vaccinators training in the districts
  02/02/19 - Final Verification of Preparedness by State level Nodal officers
  01-02/02/19 – Awareness campaigns like Miking, Jatha etc
DISTRICT LEVEL PROPOSED TIME LINE OF ACTIVITIES : NID 2019– Karnataka
  03rd February to 06th February 2019 NID days
  03/02/19 - Inauguration by In-charge Minister / DC / CEO / other dignitaries
Notes: 2

## Slide 3
  30/11/18 - State level meeting of RCHOs and District Trainers
  < 10/12/18 - Preliminary State Co-ordination meeting
  < 10/12/18 - Letter to DCs & DHOs by Principal Secretary
  < 15/12/18 – Procurement process of Marker pens & logistics to begin
  < 11/01/19 - Micro-plans Submission to State
  < 20/01/19 - State level NID Micro-plan review Workshop
  < 15/01/19 – STF meeting under Principal Secretary
  < 10/01/19- Budget allocation
  < 20/01/19 - State Steering Committee meeting under Chief Secretary
  < 20/01/19 - Procurement & distribution of vaccine & logistics - Dist HQ
  < 28/01/19 – Notification of State Nodal Officers and nodal officers meeting
  < 30/01/19 - Final Verification of Preparedness by PD(RCH)/ MD(NHM)
  < 01/02/19 - Press Conference by Health Minister, Karnataka State
  02/02/19 - Nodal Officers reaching the Districts and reviewing preparations
  03/02/19 - Inauguration by Chief Minister, Karnataka State
STATE LEVEL PROPOSED TIME LINE OF ACTIVITIES : NID 2019 – Karnataka
  03rd February to 06th February 2019 NID days
Notes: 3

## Slide 4: Discussion points:
Campaign Target
  District targets will be considered (realistic)
Budget
  Same budget from GOI as last year but only for one round
  Pulse polio head from ZP budget- For additional booths, mobile teams ; seek early approval through DHS
Printing of IEC
  District Level printing guidelines
  Explore all IEC
Marker pens
  State level procurement
bOPV Vaccine
  GOI supply

## Slide 5
Thank You